## Guidance
Salix Phase 4 PSDS Risk Register Tool
© Salix Finance 2024
A Risk Register
A risk register is a tool in risk and project management. This tool should be used to identify key risks associated with your project and appropriate mitigation techniques to lower these risk levels before they occur.
Disclaimer This tool is a guide for considering risk and mitigation. Salix recommends risks and mitigation be considered in further detail by a qualified professional.
Definitions
Likelihood - The likelihood of the risk occurring during the project timeline. Choose "Low", "Moderate", "High" from the drop down.
Impact - The level of impact the risk would have on the project should it occur during the project timeline.
Level of Risk - The overall level of risk taking into account the likelihood and impact levels. This will self populate.
Risk Owner - The person responsible for monitoring and mitigating the risk.
Type of Risk - The category of project delivery the risk falls under. Choose from the drop down. See list below.
| Risk ID | Category
| RISK.001 | Permissions/approvals
| RISK.002 | Project delivery
| RISK.003 | Cost
| RISK.004 | Feasibility
| RISK.005 | Achieving savings
| RISK.006 | Compliance
| RISK.007 | Resource
| RISK.008 | Schedule
| RISK.009 | Supply chain
| RISK.010 | Electrical supply
| RISK.011 | Other
Risk Matrix
| Impact: | Minor | Low | Moderate | High | Critical
Likelihood | Critical | Moderate | High | High | Critical | Critical
| High | Low | Moderate | High | High | Critical
| Moderate | Low | Moderate | Moderate | High | Critical
| Low | Low | Low | Low | High | Critical
| Minor | Low | Low | Low | Moderate | Moderate

## Risk Register
Salix Phase 4 Public Sector Decarbonisation Scheme Risk Register Tool
Applicant name
Updated by
Date
[6 empty] | Inherent risk (without controls) |  |  |  | Residual risk rating (with controls)
Risk ID | Risk category | Date raised | Risk description (A clear and concise statement describing the risk revent or situation.) | Risk owner | Caused by and consequences | Likelihood (The likelihood or chance that the risk event will occur) | Impact (The potential effect of the risk event if it were to occur) | Risk rating | Control(s) (The actions or measures put in place to mitigate or reduce the likelihood or impact of the risk) | Residual likelihood (The probability of the risk event occuring after control measures have been implemented) | Residual impact (The impact of the risk event after control measures have been implemented) | Residual risk rating | Risk Rating | Action
[13 empty] | Low | Proceed with manageable risk. No further governance required.
[13 empty] | Moderate | Proceed with risk but residual risk should be noted through standard governance channels.
[13 empty] | High | Consider alternative methods or additional supplemental measures. If you wish to proceed then decision should be taken to RM during a Delivery Call. Even where additional supplemental measures would not reduce the risk score, it can still be helpful to show pragmatic steps taken to manage the risk.
[13 empty] | Critical | Consider alternative supplemental measures. If you wish to proceed then RM will need to be notifed and require a Treatment Plan by the Risk Panel.
to be hidden | [8 empty] | Type of Risk
| Column1 | Scoring | [6 empty] | Schedule
| Low | 1 | [6 empty] | Cost
| Medium | 2 | [6 empty] | Feasibility
| High | 3 | [6 empty] | Achieving Savings
Compliance
Resource
Supply Chain
Electrical Supply
| Impact | [7 empty] | Permissions/Approvals
| Very High | 2 | 3 | 3 | 3 | 4 |  |  | Other
| High | 2 | 2 | 3 | 3 | 3
| Medium | 1 | 2 | 2 | 2 | 2
| Low | 1 | 1 | 1 | 2 | 2
| Very Low | 1 | 1 | 1 | 1 | 1
|  | Very Low | Low | Medium | High | Very High | Likelihood
Note on K1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be changed to High / Very High Reply: Hi @Natalie Hobbs just FYI so you can coordinate with your MMR, we are changing the wording from Severe / Critical to High / Very High :)

## Terms of Use
Salix Finance: Terms of Use for Salix Risk Register Tool
© Salix Finance 2024
Intellectual property rights
Salix is the owner or the licensee of all intellectual property rights in our tools, and in the material found within them. Salix tools are available to use free under licence. The look and feel, the integral data, the embedded calculations and algorithms, and resulting compliance guidance have been created by Salix Finance who own all the Intellectual Property contained within them for the exclusive use of its existing and potential clients. All rights are reserved. No part of the tools may be reproduced, distributed, or transmitted in any form or by any means, including photocopying, recording, or other electronic or mechanical methods, without the prior written permission of the Salix, except in the case of certain non-commercial uses permitted by copyright law. For permission requests, please write to Salix Finance Ltd at 10 South Colonnade, Canary Wharf, London, E14 4PU.

## Revision History
Revision History
Date | Version | Change | By
2024-08-01 | 1 | Creation of risk register | CP