## LL Log
Unique ID | Category/ Theme | Lesson title | Source | Date | Pos, Neg or Overview Lesson | Project/ Programme | Department or Team | Description/ Situation - What Happened? | Recommendations & Comments | Share Externally? | Value Matrix Rating | Raised by | Actions Identified | Action Owner | Action(s) Completed | Action Completed Date
| Choose a category that best reflects the nature of the lesson learned. (see fields tab for full list of options) (This is 2 separate drop downs on the submission form) | Provide a concise title that summarises the lesson. Examples could be "Improved Community Engagement Through Local Partnerships" or "Challenges in Meeting Financial Reporting Deadlines." | Identify where this lesson originated, such as a project phase, stakeholder feedback, or a mid-project review. This could also include insights identified during regular grant reporting, team meetings, or monitoring and evaluation activities. | Date when this lesson was formally recorded or logged (dd/mm/yyyy) | Specify whether the lesson reflects a positive outcome, a negative challenge, or a general observation that may be neutral but still impactful. | Reference the specific project or grant programme that this lesson relates to. | Indicate the department, team, or group primarily responsible for the area where this lesson was observed. Eg. Community Outreach Team, Finance Team | Provide a detailed description of the events or circumstances that led to this lesson. Explain the context, challenges encountered, and any key factors that contributed to this learning. | Summarise the key takeaways from the experience. Include recommendations for future projects or adjustments that may benefit others in similar situations. This could involve best practices, alternative approaches, or risk mitigation strategies | Indicate if this lesson is shareable externally, publishable, shareable with grant recipients, or for internal use only. | Rate this lesson's value by its impact and ease of implementation. High-impact, low-effort lessons are ideal for sharing | Provide the name or email of the person who identified the lesson as a contact for further inquiries. | List any specific actions that the team plans to take in response to this lesson. These might include new procedures, training sessions, resource adjustments, or policy changes. | Assign responsibility to an individual or team who will carry out these actions. This accountability ensures follow-through on valuable lessons. | Note whether identified actions have been completed. Include the completion date for tracking purposes.
LL_001 | Stakeholder Management and Communication | Challenges in face-to-face resident engagement | Observation during initial community outreach events | 2024-01-01 | Negative | SHDF Wave 2.1 | Community outreach team | We ran several community outreach events to encourage residents to sign up for the scheme. These events had low turnout and were largely unsuccessful due to the impact of Covid-19 and the cessation of previous initiatives like resident panels. Many people were reluctant to meet face-to-face. | Consider alternative outreach methods, such as mailouts, emails, or virtual events, especially during situations that limit face-to-face interactions. Identify barriers to in-person engagement early in the planning stages. | Yes | 4. High value and low effort/complexity. ​ | Alex Taylor | Assess the viability of in-person engagement for future projects. Develop contingency outreach strategies. | Community outreach team lead | Yes | 2024-10-01
LL_002 | Stakeholder Management and Communication | Effectiveness of targeted mailouts | Adaptation of outreach strategy after low turnout in initial events. | 2024-01-01 | Positive | SHDF Wave 2.1 | Community outreach team | After the low turnout of outreach events, we shifted to conducting targeted mailouts to properties identified as suitable for EWI. These letters effectively communicated: What EWI was. What residents could expect during the project. Benefits of the project, including reduced disruption compared to other measures and improved visual aesthetics post-works. This approach resulted in the successful completion of all properties. We also submitted a change request to increase the number of homes and won East Midlands Energy Efficiency Awards. | Use mailouts or similar methods to clearly communicate project details and benefits. Highlight the aesthetic and practical benefits to increase resident buy-in. Consider documenting successful strategies for future replication. | Yes | 4. High value and low effort/complexity. ​ | Alex Taylor | Document this successful approach for future projects. Share the lessons with other teams or organisations. | Community outreach team lead | Yes | 2024-10-01
LL_003 | Stakeholder Management and Communication | Importance of stock review and project size | Preliminary analysis and decision-making process for bid submission. | 2024-01-01 | Overview | SHDF Wave 2.1 | Community outreach team | A detailed review of property stock before submission was critical for the successful targeting and feasibility of the project. The decision to keep the project manageable, targeting 100 properties over two years, allowed for smoother execution and adjustments. | Conduct a thorough review of stock to ensure accurate targeting and feasibility. Keep project sizes manageable and phased for better execution and flexibility. | Yes | 4. High value and low effort/complexity. ​ | Alex Taylor | Develop structured stock review processes for future bids. Use phased approaches in project planning for better adaptability. | Community outreach team lead | Yes | 2024-10-01
LL_004
LL_005
LL_006
LL_007
LL_008
LL_009
LL_010
LL_011
LL_012
LL_013
LL_014
LL_015
LL_016
LL_017
LL_018
LL_019
LL_020
LL_021
LL_022
LL_023
LL_024
LL_025
LL_026
LL_027
LL_028
LL_029
LL_030
LL_031
LL_032
LL_033
LL_034
LL_035
LL_036
LL_037
LL_038
LL_039
LL_040
LL_041
LL_042
LL_043
LL_044
LL_045
LL_046
LL_047
LL_048
LL_049
LL_050
LL_051

## Fields
Unique ID | Category/ Theme* | *What is included within each category | Lesson title | Source | Date Entered | Pos, Neg or Overview Lesson | Project/ Programme | Department or Team | Description/ Situation | Recommendations | Share Externally? | Value Matrix Rating | Raised by | Actions Identified | Action Owner | Action(s) Completed | Action Completed Date
Assigned | Project Management and Controls | Reporting, Governance. Project Planning, Project costs, Project risks, Performance measures (KPIs), Quality Assurance, Delivery | Free Text | Free Text | Date | Positive | HUG 2 | All | Free Text | Free Text | Yes | 4. High value and low effort/complexity. ​ | Free Text | Free Text | Free Text | Yes | Date
| Stakeholder Management and Communication | Tenant Engagement, Project Engagement, Partnership Working, Media, Strategic Engagement |  |  |  | Negative | SHDF Wave 2.1 | Consortia lead |  |  | No | 3. High value and high effort. ​ |  |  |  | No
| Policy | Mixed Tenure, Planning Regulations, Tenant Engagement, Measures, Co-funding, Supply Chain, PAS2035, Other |  |  |  | Overview | SHDF Wave 2.2 | Contractors |  |  |  | 2. Low value and low effort.​
| Evaluation | Data Sharing, Quality Assurance, Impact Analysis, Information Gathering, Privacy Notice, Reporting | [5 empty] | Community outreach team |  |  |  | 1. Low value and high effort
| Analysis | Performance Measures, EPC, Data, Modelling, Grant claims, Invoicing, Purchase orders, Evidence, Financial templates | [5 empty] | Project management team
| Building and Construction | PAS2035, Trustmark, Surveys, Building, Materials, Labour, Product Innovation | [5 empty] | Resident liasion
| Commercial | Contracts, Data sharing agreements, Supply chain, Procurement, Service Level Agareements, MOU, Grant agreement, Framework
| People, Learning & Development | Capability, Labour, Training, Employment, Technical skills